## Sheet1
SDLC Phase | Deliverable | Description | ITPR Phase (MITDPs) | Required for MITDPs
Initiation | Project Charter | A Project Charter is an elevator pitch of your project objectives, project scope, and project responsibilities in order to get approval from key project stakeholders. In the charter, you should provide a short, succinct explanation of the main elements of your project before you get started. | Planning | X
Planning | Action Item Log | The Action Item Log is a kind of joint project team to-do list. It is used to record tasks that the project team members are going to do so that they don't forget to do them. Typically, this list doesn't include things that need to be done months in advance. | N/A | N/A
| Agile Implementation Plan | An Agile Implementation Plan outlines the process of executing a flexible project plan based on developing small portions of a project at a time. | Planning | X
| Agile Maturity Matrix (Assessment) | An Agile Maturity Assessment is a way to evaluate how a team is improving their ability to be agile over time. | Planning | X
| Decision Log | The Decision Log makes information available to people who were not present when the decision was made, and also to provide easy access to key information about past decisions when questions arise. | N/A | N/A
| Issues Log | An issue log is an important tool used to manage these issues and more, by helping the project team to record issues that require resolution. Along with each issue, the person or team responsible for resolving the problem is also documented | N/A | N/A
| Iteration Schedule | An iteration schedule is a series of fixed-length development periods, typically ranging from two to six weeks, called iterations. Planning an iteration involves scheduling the work to be done during an iteration and assigning individual work items to members of the team. | Planning | X
| Meeting Agenda and Minutes | An agenda gives the meeting structure and also provides you with an outline for crafting your meeting minutes and notes. | N/A | N/A
| Monthly Health Assessment Report | The Monthly Health Assessment Report provides a monthly update on the project status/accomplishments, program increments, progress, budget, milestones, risks etc. | Planning | X
| Project Management Plan | A Project management Plan is a formal, approved document that defines how the project is executed, monitored, and controlled. It may be a summary or a detailed document and may include baselines, subsidiary management plans, and other planning documents. This document is used to define the approach the project team takes to deliver the intended project management scope of the project. | Planning | X
| Project Status Report | A Project Status report is a collection of information about the current status of a project. Project status reports are used to communicate the current progress on a project to the project team and stakeholders. | N/A | N/A
| Requirements | A Requirements Document defines what is needed from the product. It states the product's purpose and what it must achieve. It does not define how to deliver or build what is needed | Planning | X
| Requirements Traceability Matrix (RTM) | The RTM is a document used to ensure that the requirements defined for a system are linked at every point during the verification process. It also ensures that they are duly tested with respect to test parameters and protocols. | Planning | X
| Responsibility Assignment Matrix (RACI) | A table that lists all stakeholders on a project and their level involvement in each task, denoted with the letters R, A, C or I. Once these roles are defined, assignments can be attributed to the roles and work can begin. | Planning | X
| Risk Log | The Risk Register provides a means of recording the identified risks, the analysis of their severity and the necessary management actions to be taken. | N/A | N/A
| Solution Roadmap | The Solution Roadmap provides a longer-term—often multiyear—view, showing the key milestones and deliverables needed to achieve the solution vision over time. While most solutions require a 1-3 year view, some larger solutions may extend this timeframe to many years. | Planning | X
| Test Case Specification | The Test Case Specification Document outlines the details of what scenarios will be tested, how they will be tested, how often they will be tested for a given feature. | N/A | N/A
| Test Plan | A Test Plan refers to a detailed document that catalogs the test strategy, objectives, schedule, estimations, deadlines, and the resources required for completing that particular project. Think of it as a blueprint for running the tests needed to ensure the software is working properly – controlled by test managers. | N/A | N/A
| Training Plan | The Training Plan is a document that communicates to management and stakeholders details of the proposed training program. | N/A | N/A
Execution | Data Conversion Plan | The Data Conversion Plan describes the strategies involved in converting data from an existing system to another hardware or software environment. | Implementation | X
| Disaster Recovery Plan | A Disaster Recovery Plan is a recorded policy and/or process that is designed to assist an organization in executing recovery processes in response to a disaster to protect business IT infrastructure and more generally promote recovery. | Implementation | X
| Disposition Plan | The Disposition Plan addresses how the various components of the system are handled at the completion of operations, including software, data, hardware, communications, and documentation. The plan also notes any future access to the system. | Implementation | X
| Interface Control Document | An Interface Control Document (ICD) provides a record of all interface information (such as drawings, diagrams, tables, and textual information) generated for a project. | Implementation | X
| Operational Readiness Assessment | An Operational Readiness Assessment ensures the operating environment is prepared to effectively support and accept the changes resulting from the project. | N/A | N/A
| System Administration Manual | The Systems Administration Manual contains key information and Standard Operating Procedures (SOPs) necessary to maintain the system effectively. | Implementation | X
| System Design Document | A System Design Document is a detailed description of the system requirements, operating environment, architecture, files and database design. It also describes the input format, different interfaces, output layouts, processing logic and detailed design. | Implementation | X
| System Security Plan | The System Security Plan provides an overview of the security requirements of the system and describe the controls in place or planned for meeting those requirements. | Implementation | X
| Test Summary Report | A Test Summary report is a quality work product/test document that formally summarizes the results of all testing. | N/A | N/A
| User Manual | The User Manual is a document that assists end-users with using a particular system, product or service seamlessly. It is also known as an instruction manual or a user guide. | N/A | N/A
Control | Change Log | A Change Log is a record of requests for change (RFCs) submitted for all changes in a project. It tracks the progress of each change from submission through review, approval, implementation and closure. | N/A | N/A
| Change Request Form | The Change Request Form is the primary tool used for requesting, approving, and documenting changes to the project and is an important piece of the change management process | N/A | N/A
Close Out | MITDP Closeout Guide | The MITDP Closeout Guide is a document used to assess the effectiveness of the system after it has been in production for a period of at least six months and ensures all final project information is documented. | Implementation | X